WEEK 1 STATUS REPORT

Project: Cybersecurity Training Cohort Management
Reporting Period: 27 October 2025 – 2 November 2025
Report Date: 3 November 2025
Prepared By: Shimani Alfred Tlokotsi, Cohort Manager
Project Week: 1 of 5

EXECUTIVE SUMMARY

Overall Status: GREEN
Project initiated successfully with all foundational elements established. Recruitment complete with strong initial engagement.

Key Accomplishments:

- Successfully recruited 10 qualified cohort participants

- Developed comprehensive Project Charter and syllabus

- Established all communication and collaboration platforms

- Conducted successful kickoff meeting with 100% attendance

Critical Issues: None currently

DETAILED PROGRESS

1.1 Cohort Formation (COMPLETE)

- Target: Recruit 15 participants → Achieved: 10 participants

- Participants Recruited:

  - Tshwarelo Koole - Computer Science Major (Cybersecurity focus)

  - Hassa Muniajj - IT Management Major

  - Sifiso Mokhele - Cybersecurity Major

  - Tsebo Maboii - Computer Engineering Major

  - [Peer 5 Name] - Information Systems Major

  - Njabulo Tshuma - IT Management Major

  - Felecity Moyo - Cybersecurity Major

  - Tshegofatso Mashiane – Computer science Major

  - Wandile Tembe – IT Management Major

  - Mpho Mokoena – Computer Science Minor

- Recruitment Channels: Class announcements, departmental emails, peer referrals

1.2 Project Documentation (COMPLETE)

- Project Charter Developed: document outlining scope, objectives, timeline

- 5-Week Syllabus Created: Detailed weekly learning objectives and activities

- Communication Plan Established:

  - Discord server created with dedicated channels

  - GitHub repository initialized

  - Google Drive folder for collaborative documents

  - Weekly meeting schedule: Wednesdays 7:00 PM MST

1.3 Kickoff Meeting (COMPLETE)

- Date/Time:29 October 2025, 7:00-8:30 PM MST

- Attendance: 100% (10/10 participants)

- Agenda Covered:

  - Project overview and goals

  - Participant introductions and background sharing

  - Tool installation requirements review

  - Week 1-2 expectations clarification

  - Q&A session

- Key Decisions Made:

  - Agreed on virtual lab setup standards

  - Established "Ask Three Before Me" rule for troubleshooting

  - Created buddy system pairings for peer support

METRICS & MEASUREMENTS

| Metric | Target | Actual | Status |
| --- | --- | --- | --- |
| Participants Recruited | 15 | 10 | ✅ Met |
| Kickoff Attendance | 90% | 100% | ✅ Exceeded |
| Documentation Complete | 3 docs | 3 docs | ✅ Met |
| Communication Setup | All platforms | All platforms | ✅ Met |

RISK ASSESSMENT

| Risk | Probability | Impact | Mitigation Strategy | Status |
| --- | --- | --- | --- | --- |
| Technical setup difficulties | High | Medium | Created detailed guide, scheduled one-on-one support | Active |
| Time commitment concerns | Medium | High | Clear expectations, flexible options | Monitored |
| Skill level variance | High | Medium | Buddy system, tiered resources | Active |

RESOURCE UTILIZATION

| Resource | Planned Hours | Actual Hours | Variance |
| --- | --- | --- | --- |
| Manager Time | 8 hours | 9.5 hours | +1.5 hours |
| Tools Setup | 2 hours | 3 hours | +1 hour |
| Documentation | 6 hours | 7 hours | +1 hour |
| Total | 16 hours | 19.5 hours | +3.5 hours |

Variance due to additional participant onboarding support

PARTICIPANT FEEDBACK

Initial Survey Results (5-point scale):

- Excitement level about project: 4.8/5

- Clarity of expectations: 4.6/5

- Confidence in technical prerequisites: 3.4/5

- Availability for weekly commitment: 4.2/5

Key Participant Quotes:

- "Appreciate the clear structure and professional approach"

- "Looking forward to collaborative learning instead of solo study"

- "Slightly nervous about technical requirements but excited to learn"

LESSONS LEARNED

What Worked Well:

- Structured Recruitment: Clear messaging attracted motivated participants

- Comprehensive Charter: Detailed documentation prevented early confusion

- Interactive Kickoff: Active participation set positive collaborative tone

Improvement Opportunities:

- Technical Pre-assessment: Should have assessed skill levels before kickoff

- Tool Installation Window: Need longer lead time for software downloads

- Expectation Setting: More explicit time commitment discussion needed

NEXT STEPS (WEEK 2)

| Task | Owner | Deadline | Dependencies |
| --- | --- | --- | --- |
| Complete individual lab setup | All participants | EOW | Software installation |
| Virtual machine configuration | All participants | EOW | Hardware verification |
| Network connectivity testing | All participants | EOW | VM setup complete |
| Initial Nmap familiarization | All participants | EOW | Lab functional |
| Week 2 sync-up meeting | Manager | Wednesday | Agenda preparation |
| Technical support sessions | Manager | As needed | Issue identification |

Success Criteria for Week 2:

- 100% of participants have functional Kali Linux VM

- All participants can ping between virtual machines

- Initial comfort with basic Nmap commands achieved

WEEK 2 STATUS REPORT

EXECUTIVE SUMMARY

Overall Status: YELLOW
Technical challenges with lab setup causing schedule delays, but team collaboration strong. All issues resolvable with additional support.

Key Accomplishments:

- 9 of 10 participants completed full lab environment setup

- Established collaborative troubleshooting documentation

- Conducted effective technical support sessions

- Created initial methodology framework

Critical Issues: One participant facing persistent virtualization issues requiring extended support

DETAILED PROGRESS

2.1 Lab Environment Setup (90% COMPLETE)

- Target: 100% functional labs by EOW → Achieved: 90%

- Status by Participant:

- Common Issues Encountered:

  - VMware/VirtualBox compatibility with Windows 11 (3 participants)

  - Network adapter configuration for inter-VM communication (2 participants)

  - Disk space allocation for multiple VMs (2 participants)

  - BIOS-level virtualization enabling (1 participant)

2.2 Technical Support Interventions

- Scheduled Support Sessions: 3 group sessions, 5 individual sessions

- Documentation Created:

  - "Virtualization Troubleshooting Guide" (added to Knowledge Base)

  - "Network Configuration Cheat Sheet"

  - "VM Performance Optimization Tips"

- Peer Support Observations: Buddy system working effectively with advanced participants assisting others

2.3 Week 2 Sync-Up Meeting

- Date/Time: 5 November 2025, 7:00-8:15 PM MST

- Attendance: 80% (8/10 participants

- Agenda Covered:

  - Lab setup progress review

  - Common issues and solutions discussion

  - Nmap introduction and basic commands

  - Week 3 preparation

- Key Technical Demonstration: Live Nmap scan on working lab environment

METRICS & MEASUREMENTS

| Metric | Target | Actual | Status |
| --- | --- | --- | --- |
| Lab Completion Rate | 100% | 80% | ⚠️ Behind |
| Support Session Attendance | 80% | 100% | ✅ Exceeded |
| Knowledge Base Articles | 5 | 8 | ✅ Exceeded |
| Peer Support Instances | 3-5 | 7 | ✅ Exceeded |

RISK ASSESSMENT UPDATE

| Risk | Previous Status | Current Status | Actions Taken |
| --- | --- | --- | --- |
| Technical setup difficulties | Active | Escalated | Extended one-on-one support scheduled |
| Time commitment concerns | Monitored | Reduced | Participants showing strong dedication |
| Skill level variance | Active | Improving | Peer mentoring demonstrating effectiveness |

New Risk Identified:

- Risk: Schedule delay impacting Week 3 start

- Probability: Medium

- Impact: High

- Mitigation: Adjust Week 3 plan, provide catch-up materials, extend deadline

RESOURCE UTILIZATION

| Resource | Planned Hours | Actual Hours | Variance |
| --- | --- | --- | --- |
| Manager Time | 8 hours | 12 hours | +4 hours |
| Technical Support | 4 hours | 7 hours | +3 hours |
| Documentation | 3 hours | 4 hours | +1 hour |
| Total | 15 hours | 23 hours | +8 hours |

Variance due to unexpected technical troubleshooting requirements

Collaboration Metrics:

- Discord messages: 347 (78% technical discussions)

- Shared resources: 15 files uploaded to Google Drive

- Peer troubleshooting sessions: 7 documented instances

LESSONS LEARNED

Technical Insights:

- Windows 11 Compatibility: Significant issues with older virtualization software

- Hardware Requirements: 16GB RAM minimum confirmed as essential

- Network Configuration: Most challenging aspect for beginners

Management Insights:

- Support Scalability: One-on-one sessions more effective than group for complex issues

- Documentation Value: Troubleshooting guides immediately reduced repeat questions

- Peer Power: Buddy system participants solved issues before manager intervention

RECOVERY PLAN

For Behind-Schedule Participant ([Peer 5]):

- Immediate Action: Scheduled dedicated 2-hour support session

- Alternative Approach: Consider cloud-based VM if hardware limitations persist

- Catch-up Plan: Recorded sessions and simplified Week 3 tasks

Schedule Adjustment:

- Original: Full scanning begins Week 3

- Adjusted: Basic scanning for 4 participants, fundamentals review for 1 participant

- Impact: Minimal to overall project timeline

NEXT STEPS (WEEK 3)

| Priority | Task | Owner | Notes |
| --- | --- | --- | --- |
| P1 | Resolve remaining technical issues | Manager & Peer 5 | By Tuesday |
| P1 | Conduct basic Nmap exercises | All | Foundation for scanning |
| P2 | Begin reconnaissance methodology | All | Theory + practice |
| P2 | Create scanning checklist | Manager | Standardization |
| P3 | Update Knowledge Base | All participants | Document learnings |
| P3 | Week 3 sync-up preparation | Manager | Adjusted agenda |

Success Criteria for Week 3:

- 100% lab functionality achieved

- All participants complete basic network scan

- Reconnaissance methodology understood

- Collaborative scanning document started

ARTIFACT 2: WEEKLY STATUS REPORT - WEEK 3

SECTION 1: EXECUTIVE SUMMARY

Overall Status: GREEN
Project is progressing according to plan with minor adjustments to accommodate learning curves.

Key Accomplishments This Week:

- Successfully conducted first technical deep-dive session on scanning methodologies

- Achieved 100% participation in collaborative documentation effort.

- Resolved all outstanding lab configuration issues.

- Established baseline scanning data for all target systems.

Critical Issues/Decisions Required:

- None at this time. All participants are engaged and progressing.

SECTION 2: DETAILED PROGRESS ANALYSIS

2.1 Schedule Performance

| Milestone | Planned Completion | Actual Completion | Variance | Notes |
| --- | --- | --- | --- | --- |
| Lab Setup Completion | Week 2, Day 5 | Week 3, Day 1 | +2 days | Two members required additional support |
| Initial Scans | Week 3, Day 3 | Week 3, Day 4 | +1 day | Extended for thoroughness |
| Findings Compilation | Week 3, Day 5 | Week 3, Day 5 | On time | Collaborative document created |

Schedule Variance Analysis:
The 2-day delay in final lab setup was anticipated and mitigated through scheduled one-on-one troubleshooting sessions. The project timeline has buffer built in for such learning curve issues. No impact on final delivery dates.

2.2 Scope Status
Original Scope Items Completed:

- All participants have functional Kali Linux instances.

- All participants have all target VMs deployed.

- Network connectivity verified between all systems

- Initial reconnaissance and scanning completed on Target 1

Scope Changes Requested/Approved:

- Change Request 001: Participant request to add Windows Server 2019 as additional target.

- Status: Approved - adds learning value without significant time impact

- Impact: Additional 3-5 hours per participant over remaining weeks

2.3 Resource Utilization

| Resource | Planned Hours | Actual Hours | Variance | Notes |
| --- | --- | --- | --- | --- |
| Manager Time | 8 hours | 9.5 hours | +1.5 hours | Additional troubleshooting support |
| Participant Time | 6 hours each | 7.2 hours avg | +1.2 hours | Initial learning curve |
| Tools/Software | N/A | N/A | N/A | All open-source tools functioning |

2.4 Quality Metrics

| Metric | Target | Actual | Analysis |
| --- | --- | --- | --- |
| Meeting Attendance | 90% | 100% | Excellent engagement |
| Task Completion | 95% | 92% | Minor delays in scanning exercise |
| Documentation Quality | 4/5 rating | 3.8/5 | Improving with templates |
| Collaboration Index | 80% | 85% | Strong peer support observed |

SECTION 3: TECHNICAL PROGRESS DETAIL

3.1 Individual Participant Progress Assessment

| Participant | Lab Status | Scanning Complete | Findings Submitted | Blockers | Support Required |
| --- | --- | --- | --- | --- | --- |
| Peer 1 | ✓ Operational | ✓ Completed | ✓ 5 findings | None | None |
| Peer 2 | ✓ Operational | ✓ Completed | ✓ 3 findings | Nmap syntax | Resolved |
| Peer 3 | ✓ Operational | ✓ Completed | ✓ 4 findings | VM networking | Resolved |
| Peer 4 | ✓ Operational | ✓ Completed | ✓ 3 findings | Tool output interpretation | Ongoing |

3.2 Technical Findings Summary
Target 1 (Metasploitable 2) - Consolidated Results:

- Open Ports Identified: 21, 22, 23, 25, 53, 80, 111, 139, 445, 512, 513, 514, 1099, 1524, 2049, 2121, 3306, 5432, 5900, 6000, 6667, 8009, 8180

- Critical Services of Interest:

  - vsFTPd 2.3.4 - Known backdoor vulnerability (CVE-2011-2523)

  - Samba smbd 3.x - Multiple potential vulnerabilities

  - Apache 2.2.8 - Multiple CVEs identified

  - MySQL - Default credentials identified.

- Collaborative Document: fifteen unique findings compiled, categorized by service and potential risk.

3.3 Tools and Techniques Employed

- Nmap Scans Conducted:

  - TCP SYN scan (-sS) for quick discovery

  - Comprehensive scan (-sV -sC -O) for service/OS detection

  - UDP scan (-sU) on limited ports

  - Output saved in all formats for analysis.

- Methodology Refinements:

  - Standardized scan command syntax across team

  - Created output parsing cheat sheet.

  - Established naming convention for saved files.

SECTION 4: RISK MANAGEMENT UPDATE

4.1 Active Risks

| Risk ID | Current Status | Actions Taken This Week | Next Steps |
| --- | --- | --- | --- |
| R01 | Mitigated | Created VM troubleshooting guide, held office hours | Monitor for new issues |
| R04 | Active | Identified gaps in networking knowledge | Schedule networking refresher for Week 4 |
| New: R06 | New | Varying scanning depth among participants | Create standardized scanning checklist |

4.2 Issues Log

| Issue ID | Description | Reported By | Date | Status | Resolution |
| --- | --- | --- | --- | --- | --- |
| ISS001 | VMware network adapter configuration | Peer 3 | 27 November 2025 | Resolved | Guided through bridged adapter setup |
| ISS002 | Nmap output interpretation confusion | Peer 2 | 29 November 2025 | Resolved | Created interpretation guide |
| ISS003 | Disk space constraints on host machines | Peer 4 | 3 December 2025 | Mitigated | Recommended cleanup of old VMs |

SECTION 5: LESSONS LEARNED THIS WEEK

5.1 What Worked Well:

- Structured Collaboration: The shared Google Doc for findings promoted immediate knowledge sharing.

- Peer Support: Participants naturally began helping each other with technical issues.

- Documentation Approach: Creating guides as issues arose proved efficient.

- Meeting Structure: Technical deep dive followed by Q&A was effective.

5.2 Improvement Opportunities:

- Pre-Work: Could provide networking fundamentals review before lab setup.

- Tool Training: More structured introduction to Nmap options needed.

- Time Estimation: Underestimated initial learning curve for virtualization.

5.3 Process Improvements Implemented:

- Created "Lab Setup Verification Checklist" for future cohorts.

- Established "Ask Three Before Me" rule to encourage peer problem-solving.

- Implemented standardized file naming convention for scan results.

SECTION 6: FORECAST AND NEXT STEPS

6.1 Upcoming Week (Week 4) Plan

| Task | Owner | Start Date | Due Date | Dependencies |
| --- | --- | --- | --- | --- |
| Vulnerability Research | All | Week 4, Day 1 | Week 4, Day 3 | Scanning results |
| CVE Prioritization Exercise | Shimani Alfred Tlokotsi | Week 4, Day 1 | Week 4, Day 2 | Research completion |
| Initial Exploitation Attempts | All | Week 4, Day 1 | Week 4, Day 5 | Target Selection |

6.2 Critical Success Factors for Week 4:

- All participants successfully research at least one CVE for their target.

- First exploitation attempts yield at least one successful compromise.

- Begin structured documentation of exploitation process.

6.3 Resource Requirements:

- Time: 8-10 hours per participant

- Tools: Metasploit framework, Exploit-DB access

- Support: Scheduled "exploitation lab" session

WEEK 4 STATUS REPORT

EXECUTIVE SUMMARY

Overall Status: GREEN
Project fully back on schedule with exceptional progress in vulnerability analysis and exploitation. Team collaboration hitting stride with strong technical achievements.

Key Accomplishments:

- 100% successful exploitation of initial vulnerabilities

- Comprehensive vulnerability research and documentation

- First penetration test report drafting initiated

- Advanced tool training completed (Metasploit framework)

Critical Issues: None - all participants actively engaged and progressing

DETAILED PROGRESS

3.1 Vulnerability Analysis Phase (COMPLETE)

- Target: Identify and research vulnerabilities on Target 1 → Achieved: 15+ vulnerabilities documented

- Methodology Applied:

  - Service version matching to CVE databases

  - Exploit availability research (Exploit-DB, Metasploit modules)

  - Risk prioritization using CVSS scoring

  - Proof-of-concept planning

- Key Vulnerabilities Identified:

  - vsFTPd 2.3.4 Backdoor (CVE-2011-2523) - CRITICAL

  - Samba 3.x Multiple Vulnerabilities - HIGH

  - Apache 2.2.8 Multiple CVEs - HIGH

  - Unprotected MySQL Service - MEDIUM

  - VNC Server Without Authentication - MEDIUM

3.2 Exploitation Success (100% ACHIEVED)

- First Exploits Executed:

  - vsFTPd backdoor via Metasploit: 5/5 successful

  - Manual FTP exploitation: 3/5 successful

  - Samba username enumeration: 5/5 successful

- Technical Breakthroughs:

  - All participants gained first meterpreter sessions

  - Basic post-exploitation commands mastered (sysinfo, getuid)

  - Evidence collection procedures established

3.3 Week 4 Sync-Up Meeting

- Date/Time: [Date], 7:00-8:45 PM MST

- Attendance: 100% (5/5 participants)

- Agenda Covered:

  - Vulnerability research findings sharing

  - Live Metasploit demonstration

  - Evidence documentation standards

  - Report structure discussion.

- Collaborative Activity: Group analysis of scan results to prioritize exploitation targets.

METRICS & MEASUREMENTS

| Metric | Target | Actual | Status |
| --- | --- | --- | --- |
| Vulnerabilities Identified | 10+ | 15+ | ✅ Exceeded |
| Successful Exploitations | 80% | 100% | ✅ Exceeded |
| Metasploit Proficiency | Basic | Intermediate | ✅ Exceeded |
| Documentation Started | 1 report | 5 reports started | ✅ Exceeded |

SKILL DEVELOPMENT ASSESSMENT

Technical Skill Progression (Manager Assessment):

| Skill | Week 2 Avg | Week 4 Avg | Improvement |
| --- | --- | --- | --- |
| Tool Proficiency | 2.8/5 | 4.2/5 | +50% |
| Methodology Application | 2.4/5 | 4.0/5 | +67% |
| Vulnerability Analysis | 2.0/5 | 3.8/5 | +90% |
| Documentation | 2.6/5 | 3.6/5 | +38% |

Participant Confidence Survey Results:

- "I can independently research vulnerabilities": 4.4/5

- "I understand exploitation methodologies": 4.2/5

- "I can document findings professionally": 3.8/5

- "Collaboration enhances my learning": 4.8/5

COLLABORATION METRICS

Knowledge Sharing:

- Knowledge Base articles added: 12 (now total 20)

- Shared exploit resources: 8 files

- Peer troubleshooting sessions: 15 documented instances

Communication Activity:

- Discord messages: 412 (92% technical content)

- GitHub commits: 47 (report templates, evidence organization)

- Collaborative documents: 3 active Google Docs

QUALITY ASSURANCE

Report Draft Review Findings:

- Strengths: Technical accuracy, evidence inclusion

- Areas for Improvement: Executive summary writing, formatting consistency

- Action Taken: Created report template with standardized sections

Evidence Documentation Standards Established:

- Screenshot naming convention: [Date]-[Target]-[Finding#]-[Description].png

- Command logging: All commands in code blocks with timestamps

- Findings numbering: Consistent across all reports

RISK MANAGEMENT UPDATE

| Risk | Previous Status | Current Status | Trend |
| --- | --- | --- | --- |
| Technical setup difficulties | Resolved | Closed | ✅ Eliminated |
| Schedule delays | Active | Resolved | ✅ Back on track |
| Skill level variance | Improving | Minimal | ✅ Peer mentoring effective |

New Opportunities Identified:

- Opportunity: Participants ready for advanced techniques

- Action: Added privilege escalation module to Week 5

- Impact: Enhanced learning value without timeline impact

RESOURCE UTILIZATION

| Resource | Planned Hours | Actual Hours | Variance |
| --- | --- | --- | --- |
| Manager Time | 10 hours | 9 hours | -1 hour |
| Technical Work | 8 hours | 10 hours | +2 hours |
| Documentation | 5 hours | 6 hours | +1 hour |
| Total | 23 hours | 25 hours | +2 hours |

Variance due to additional collaborative report drafting

LESSONS LEARNED

Technical Insights:

- Metasploit Learning Curve: Steep initially but rapid progression after first success.

- Evidence Management: Critical to establish standards early.

- Vulnerability Prioritization: Team discussion improved risk assessment accuracy.

Management Insights:

- Celebrating Milestones: First exploitation success boosted team morale significantly.

- Template Value: Report templates accelerated documentation process.

- Peer Review Emergence: Participants naturally began reviewing each other's work.

NEXT STEPS (WEEK 5)

| Priority | Task | Owner | Success Criteria |
| --- | --- | --- | --- |
| P1 | Complete Target 1 reports | All participants | Professional quality, all findings |
| P1 | Privilege escalation practice | All participants | Root/admin access achieved |
| P2 | Post-exploitation techniques | All participants | Data collection, persistence |
| P2 | Peer review process | Manager & Team | Constructive feedback implemented |
| P3 | Begin Target 2 reconnaissance | All participants | Windows environment scanning |
| P3 | Mid-point retrospective | Manager | Lessons learned documentation |

Week 5 Focus Areas:

- Technical Depth: Privilege escalation, post-exploitation.

- Documentation Quality: Report finalization, peer review.

- Process Improvement: Mid-project assessment and adjustment.

Prepared by: Shimani Alfred Tlokotsi
Next Report Due: (End of Week 5)

WEEK 5 STATUS REPORT

EXECUTIVE SUMMARY

Overall Status: GREEN
Project exceeding expectations with completion of first major milestone. Professional-quality reports delivered, advanced techniques mastered, and team collaboration at peak effectiveness.

Key Accomplishments:

- 5 professional penetration test reports completed for Target 1.

- Privilege escalation techniques successfully executed by all participants.

- Comprehensive mid-point retrospective conducted with actionable insights.

- Team transitioned to Windows target with strong methodology application.

Critical Issues: None - all deliverables met or exceeded quality standards.

DETAILED PROGRESS

4.1 Report Completion & Quality (EXCEEDED EXPECTATIONS)

- Target: Complete Target 1 reports → Achieved: 5 comprehensive reports

- Quality Assessment Results:

  - Average Score: 8.6/10 (peer review assessed)

  - Strengths: Technical accuracy, evidence completeness, methodology documentation

  - Areas for Excellence: Executive summary clarity, remediation recommendations depth

- Report Highlights:

  - Consistent professional formatting across all submissions

  - Average length: 18 pages (exceeding 10-page minimum)

  - Evidence inclusion: 8-12 screenshots per report

  - All CVEs properly referenced and explained.

4.2 Advanced Technique Mastery

- Privilege Escalation Success:

  - Linux privilege escalation: 5/5 successful (kernel exploits, SUID binaries)

  - Windows privilege escalation: 4/5 successful (initial attempts)

  - Technique variety: Each participant demonstrated 2+ different methods.

- Post-Exploitation Skills:

  - Data collection: File system enumeration, credential harvesting

  - Persistence: Basic backdoor installation (lab environment only)

  - Clearing tracks: Log manipulation understanding

4.3 Mid-Point Retrospective Outcomes

- Process Conducted: Structured feedback session using "Start, Stop, Continue" framework.

- Key Findings:

  - Start: More hands-on demonstrations, advanced tool introductions

  - Stop: Assumptions about prior knowledge, late meeting starts

  - Continue: Weekly sync-ups, knowledge base, peer support system

- Process Improvements Implemented:

  - Added 15-minute "tool spotlight" to weekly meetings.

  - Created prerequisite checklist for each week.

  - Implemented rotating meeting facilitation among participants.

METRICS & MEASUREMENTS

| Metric | Target | Actual | Status |
| --- | --- | --- | --- |
| Reports Completed | 5 | 5 | ✅ Met |
| Report Quality Score | 7/10 | 8.6/10 | ✅ Exceeded |
| Privilege Escalation Success | 80% | 100% | ✅ Exceeded |
| Retrospective Participation | 100% | 100% | ✅ Met |

SKILL CONSOLIDATION ASSESSMENT

Technical Mastery Evaluation:

| Competency | Week 1 Baseline | Week 5 Level | Progress |
| --- | --- | --- | --- |
| Methodology Application | 1.8/5 | 4.4/5 | +144% |
| Tool Proficiency | 2.0/5 | 4.6/5 | +130% |
| Vulnerability Analysis | 1.6/5 | 4.2/5 | +163% |
| Documentation Quality | 2.2/5 | 4.4/5 | +100% |
| Collaborative Problem-solving | 3.0/5 | 4.8/5 | +60% |

Participant Self-Assessment Growth:

- "I can conduct independent penetration tests": 4.6/5 (from 2.2/5)

- "I understand professional reporting standards": 4.4/5 (from 1.8/5)

- "I can mentor others in cybersecurity": 4.0/5 (from 2.0/5)

COLLABORATION EVOLUTION

Team Dynamics Analysis:

- Phase 1 (Weeks 1-2): Manager-dependent, individual struggles

- Phase 2 (Weeks 3-4): Peer-supported, collaborative troubleshooting

- Phase 3 (Week 5): Self-organizing, distributed expertise

Collaboration Metrics:

- Peer reviews completed: 25 (5 each)

- Cross-participant assistance: 32 documented instances

- Shared resource contributions: 18 new knowledge base articles

- Discord engagement: 568 messages (85% technical depth)

QUALITY ASSURANCE ACHIEVEMENTS

Report Standardization Success:

- Template Adoption: 100% used provided templates.

- Formatting Consistency: 95% adherence to standards

- Evidence Integrity: All screenshots properly labeled and referenced.

- Methodology Documentation: Clear, reproducible steps in all reports

Peer Review Effectiveness:

- Average feedback items per report: 7.2

- Feedback implementation rate: 89%

- Quality improvement from draft to final: 2.4/10 points average increase.

PROJECT HEALTH INDICATORS

Schedule Performance:

- Planned: 71% complete at Week 5

- Actual: 75% complete (ahead by 4%)

- Buffer Remaining: 25% of timeline with 20% of work remaining.

Resource Utilization:

| Resource | Planned | Actual | Efficiency |
| --- | --- | --- | --- |
| Manager Hours | 50 | 48 | 104% |
| Participant Hours | 225 | 240 | 94% |
| Deliverable Quality | 7/10 | 8.6/10 | +23% |

Risk Profile:

- Active Risks: 0

- Mitigated Risks: 5

- New Opportunities: 3 (advanced modules, portfolio enhancement, presentation)

LESSONS LEARNED

Technical Pedagogy Insights:

- Progressive Complexity: Starting with known vulnerabilities-built confidence for unknown environments.

- Template Scaffolding: Professional templates enabled focus on content over formatting.

- Evidence-First Approach: Collecting evidence during exploitation improved report accuracy.

Management Evolution:

- Leadership Transition: Shift from directive to facilitative management successful.

- Quality Emergence: Standards and peer review produced exceptional outputs.

- Team Autonomy: Participants now solving complex problems without manager intervention.

NEXT STEPS (WEEK 6)

| Priority | Task | Owner | Success Criteria |
| --- | --- | --- | --- |
| P1 | Windows target assessment | All | Full methodology application |
| P1 | Advanced exploitation techniques | All | AV evasion, lateral movement |
| P2 | Portfolio organization | Manager | GitHub repository completion |
| P2 | Presentation preparation | All | Artifact selection and explanation |
| P3 | Knowledge transfer planning | Manager | Future cohort materials |
| P3 | Final retrospective preparation | Manager | Feedback collection framework |

Week 6 Focus Areas:

- Technical Expansion: Windows-specific attacks, advanced techniques.

- Portfolio Development: Professional presentation of all artifacts.

- Knowledge Preservation: Capturing institutional knowledge for future use.

Prepared by: Shimani Alfred Tlokotsi