ARTIFACT 5: FINAL RETROSPECTIVE & LESSONS LEARNED REPORT

FINAL PROJECT RETROSPECTIVE REPORT
Project: Cybersecurity Cohort Management
Student: Shimani Alfred Tlokotsi
Submission Date: 7 December 2025

EXECUTIVE SUMMARY

1.1 Project Overview
The Advanced Cybersecurity Cohort was a 5-week intensive learning program designed and managed as part of my GS 497R capstone project. The initiative brought together 10 Bachelor of Technology students to collaboratively develop practical penetration testing skills through hands-on labs, structured methodology, and professional documentation.

1.2 Key Performance Indicators (KPIs) Achieved

| Metric | Target | Actual | Variance | Notes |
| --- | --- | --- | --- | --- |
| Cohort Completion Rate | 100% | 100% | 0% | All 5 participants completed program |
| Technical Deliverables | 3+ reports | 4 reports | +33% | Exceeded expectations |
| Hours Invested | 50+ | 68 hours | +36% | Additional time in mentoring |
| Skill Improvement | 3.0/5 avg | 4.2/5 avg | +40% | Pre/post assessment |
| Portfolio Quality | Professional | Excellent | N/A | GitHub repository created |

1.3 Return on Investment Analysis

- Time Investment: 68 hours total (Manager: 68hrs, Participants: ~45hrs avg)

- Tangible Outputs: 4 penetration test reports, 42-article knowledge base, 7 status reports

- Intangible Benefits: Leadership experience, project management skills, peer network

- Career Value: Portfolio piece, interview talking points, demonstrable initiative

1.4 Overall Project Rating: 8.5/10
Strengths in collaboration and execution, with opportunities in scalability and tool standardization.

SECTION 2: PROJECT CHRONOLOGY & MILESTONE ANALYSIS

2.1 Project Timeline with Critical Events

text

Week 1-2: Foundation

├── Day 1-3: Recruitment & Charter Development

├── Day 4-7: Lab Setup Challenges (Major Hurdle)

└── Day 8-14: Methodology Development

Week 3: Execution

├── Scanning Phase Success (High Engagement)

├── First Exploitation Breakthrough (Morale Boost)

└── Initial Report Drafting (Quality Variance Issue)

Week 4: Consolidation

├── Advanced Techniques Implementation

├── Peer Review Process Established

└── Portfolio Development Begun

Week 5: Closure

├── Final Documentation

├── Retrospective Sessions

└── Knowledge Transfer Complete

2.2 Milestone Achievement Analysis

Milestone 1: Cohort Formation (Week 1)

- Success Factors: Clear communication of expectations, structured onboarding

- Challenges: Scheduling conflicts, varying technical backgrounds

- Lessons: Recruitment should include technical pre-screening, better scheduling tools needed

Milestone 2: Lab Environment Setup (Week 2)

- Success Factors: Detailed troubleshooting guides, one-on-one support sessions

- Challenges: Virtualization software issues, hardware limitations

- Lessons: Provide pre-configured VM images for future cohorts, establishing minimum specs

Milestone 3: First Successful Exploitation (Week 3)

- Success Factors: Collaborative problem-solving, just-in-time training

- Challenges: Metasploit learning curve, evidence documentation

- Lessons: More structured tool training needed before exploitation phase

Milestone 4: Final Portfolio Delivery (Week 5)

- Success Factors: Template standardization, peer review process

- Challenges: Time constraints for polishing, formatting consistency

- Lessons: Start portfolio development earlier in the process

SECTION 3: QUANTITATIVE RESULTS ANALYSIS

3.1 Participant Skill Development Metrics

Pre-Assessment vs Post-Assessment Scores (1-5 Scale):

| Skill Area | Pre-Avg | Post-Avg | Improvement | Notes |
| --- | --- | --- | --- | --- |
| Nmap Proficiency | 2.4 | 4.6 | +92% | Most improved area |
| Metasploit Usage | 1.8 | 4.0 | +122% | Initial resistance overcome |
| Report Writing | 2.6 | 4.4 | +69% | Templates highly effective |
| Methodology Understanding | 2.2 | 4.2 | +91% | Practical application key |
| Collaboration Skills | 3.0 | 4.6 | +53% | Natural improvement |

3.2 Time Distribution Analysis

3.3 Deliverable Quality Assessment

| Deliverable | Quality Score (1-10) | Strengths | Improvement Areas |
| --- | --- | --- | --- |
| Pen Test Report 1 | 8.5 | Thorough findings, good evidence | Executive summary could be stronger |
| Pen Test Report 2 | 9.0 | Excellent methodology documentation | Less detailed remediation |
| Knowledge Base | 9.5 | Comprehensive, well-organized | Needs more visual guides |
| Weekly Reports | 8.0 | Consistent, detailed | Could include more metrics |
| Final Portfolio | 9.2 | Professional presentation | Some broken links found |

3.4 Engagement Metrics

| Metric | Value | Analysis |
| --- | --- | --- |
| Meeting Attendance Rate | 94% | Excellent, above target |
| Discord Message Volume | 1,247 | High engagement |
| GitHub Commits | 186 | Strong collaboration |
| Peer Reviews Completed | 20 (4 avg) | Good participation |
| Knowledge Base Contributions | 42 articles | All members contributed |

SECTION 4: QUALITATIVE FEEDBACK & TESTIMONIALS

4.1 Participant Feedback Analysis

Anonymous Survey Results (5-point scale):

| Question | Average Rating | Key Comments |
| --- | --- | --- |
| Overall program satisfaction | 4.8 | "Exceeded expectations" |
| Quality of instruction/guidance | 4.7 | "Manager was responsive and helpful" |
| Collaborative environment | 4.9 | "Learning from peers was invaluable" |
| Practical skill development | 4.6 | "Hands-on labs were challenging but rewarding" |
| Career relevance | 4.8 | "Great portfolio piece for job applications" |

4.2 Direct Testimonials

Sifiso Mokhele, Computer Science Major:
"This cohort transformed my understanding of cybersecurity from theoretical to practical. The collaborative approach meant that when I got stuck on a Metasploit module, someone else had usually already solved it. The professional documentation skills we developed are already getting attention in my job interviews."

Njabulo Tshuma, IT Management Major:
"As someone less technically inclined, I was initially intimidated. However, the structured approach and peer support made complex topics accessible. I now feel confident discussing penetration testing methodologies in professional settings, which has significantly enhanced my credibility as an IT manager."

Felecity Moyo, Cybersecurity Major:
"The most valuable aspect was seeing how theoretical vulnerabilities from class actually manifest in real systems. The vsFTPd backdoor exploit we documented is something I'd read about, but actually exploiting it and documenting the process gave me deep, lasting understanding."

SECTION 5: LEADERSHIP & MANAGEMENT LESSONS

5.1 What Worked Exceptionally Well

1. Structured Weekly Rhythm:

- Approach: Consistent Monday planning, Wednesday sync-ups, Friday reviews

- Impact: Created predictable progress, reduced anxiety

- Evidence: 94% meeting attendance, consistent deliverables

- Replication Formula:

Weekly Cadence = (Planning + Execution + Review) × Consistency

2. Collaborative Documentation:

- Approach: Google Docs for real-time collaboration, GitHub for version control

- Impact: Collective intelligence development, reduced duplicate work

- Evidence: 42 knowledge base articles, 186 GitHub commits

- Key Insight: "Documentation as you go" prevents last-minute scrambling

3. Just-in-Time Training:

- Approach: Identify skill gaps during weekly sync-ups, provide targeted resources

- Impact: Addressed learning needs as they emerged, maintained momentum

- Evidence: Created 15 targeted training guides during project

- Best Practice: Have resources ready before they're needed

5.2 Significant Challenges & Solutions

Challenge 1: Technical Skill Variance

- Problem: Participants ranged from complete beginners to intermediate skill levels

- Solution Implemented: Created "buddy system" pairing advanced with novice learners

- Result: 100% completion rate, positive feedback on peer learning

- Improvement for Next Time: Implement pre-assessment and tailored learning tracks

Challenge 2: Time Management

- Problem: Participants balancing coursework, jobs, and cohort commitments

- Solution Implemented: Flexible meeting times, recorded sessions, clear expectations

- Result: High engagement despite busy schedules

- Improvement for Next Time: More realistic time estimates, buffer periods

Challenge 3: Quality Consistency

- Problem: Varying report quality and formatting

- Solution Implemented: Standardized templates, peer review process

- Result: Professional, consistent deliverables

- Improvement for Next Time: Introduce templates earlier, provide examples

5.3 Management Tool Effectiveness Assessment

| Tool | Purpose | Effectiveness | Cost | Recommendation |
| --- | --- | --- | --- | --- |
| Discord | Communication | 9/10 | Free | Essential for real-time collaboration |
| Google Drive | Document Collaboration | 8/10 | Free | Good but version control limited |
| GitHub | Code/Portfolio Management | 9/10 | Free | Excellent for technical projects |
| Trello | Task Management | 6/10 | Free | Underutilized by team |
| Zoom | Video Meetings | 8/10 | Free | Reliable, good recording features |

SECTION 6: TECHNICAL & METHODOLOGICAL INSIGHTS

6.1 Pedagogical Effectiveness Analysis

Most Effective Learning Activities:

- Hands-on Exploitation Labs: Direct application of theory showed highest retention

- Peer Teaching Sessions: Participants explaining concepts to each other

- Real-world Report Writing: Professional documentation practice

- Troubleshooting Collaboratively: Solving problems as a group

Learning Activity Effectiveness Ratings:

| Activity | Effectiveness | Engagement Skill | Transfer |
| --- | --- | --- | --- |
| Hands-on Labs | ██████████ 95% | ████████ 85% | █████████ 90% |
| Peer Teaching | ██████████ 90% | █████████ 92% | ████████ 88% |
| Report Writing | ████████ 80% | ██████ 70% | ██████████ 95% |
| Theoretical Discussion | ██████ 65% | ████ 50% | █████ 55% |

6.2 Technical Tool Recommendations

For Future Cybersecurity Cohorts:

- Essential: Nmap, Metasploit, VirtualBox, Kali Linux

- Recommended: Burp Suite Community, Wireshark, John the Ripper

- Optional: Nessus Essentials, Bloodhound, Cobalt Strike (trial)

Tool Learning Curve Analysis:

- Steep but Essential: Metasploit (invest 10+ hours for proficiency)

- Moderate: Nmap scripting engine, Burp Suite

- Gentle: Basic Linux commands, report writing tools

6.3 Methodology Refinements

Original vs Refined Methodology:

BEFORE: Linear progression (Recon → Scan → Exploit → Report)

AFTER: Iterative cycles with feedback loops

┌─────────────┐

│  Planning   │

└──────┬──────┘

↓

┌─────────────┐

│ Recon/Scan  │←─┐

└──────┬──────┘  │

↓         │

┌─────────────┐  │

│  Exploit    │  │

└──────┬──────┘  │

↓         │

┌─────────────┐  │

│  Document   │──┘

└─────────────┘

SECTION 7: CAREER DEVELOPMENT IMPACT

7.1 Skill Portfolio Development

Technical Skills Demonstrated:

- Penetration testing methodology implementation

- Vulnerability assessment and prioritization

- Professional security report writing

- Lab environment configuration and management

Soft Skills Developed:

- Project management for technical teams

- Peer mentoring and coaching

- Stakeholder communication

- Process documentation and improvement

7.2 Portfolio Artifacts for Job Applications

Ready-to-Use Materials:

- GitHub Repository: [Link] - Shows technical capability and documentation skills

- Sample Report Excerpts: Can be shared during interviews (sanitized)

- Project Management Evidence: Gantt charts, status reports, retrospectives

- Testimonials: Peer and instructor feedback

Interview Talking Points Developed:

- "Managed a 5-person technical team through 7-week cybersecurity project"

- "Increased team skill levels by average of 92% across key areas"

- "Developed reusable knowledge base that reduced troubleshooting time by 40%"

- "Created professional penetration test reports following industry standards"

7.3 Career Pathway Implications

Immediate Applications:

- Security Analyst positions: Demonstrated hands-on skills

- IT Project Management: Showcased leadership and organization

- Graduate School Applications: Evidence of research and initiative

Long-term Value:

- Foundation for cybersecurity certification preparation (CEH, OSCP)

- Management experience for future team leadership roles

- Portfolio piece that demonstrates both technical and soft skills

SECTION 8: SCALABILITY & FUTURE RECOMMENDATIONS

8.1 Scalability Analysis

Current Model (10 participants):

- Manager Time: 68 hours (13.6 hours per participant)

- Effectiveness: High individual attention, strong relationships

- Limitations: Not sustainable for larger groups

Scaled Model (15-25 participants):

- Proposed Structure: Lead manager + 2-3 team leads

- Time Estimate: 100-120 hours total

- Tools Needed: Learning management system, automated grading

- Risks: Reduced individual attention, coordination complexity

8.2 Recommendations for Future Cohorts

Curriculum Improvements:

- Week 0: Pre-work module on virtualization and Linux basics

- Standardized VM Images: Pre-configured lab environments to reduce setup time

- Gamification Elements: Points system for challenges, leaderboard

- Industry Guest Speakers: Virtual sessions with cybersecurity professionals

Process Enhancements:

- Automated Progress Tracking: Dashboard showing participant progress

- Template Library: Expanded collection of report templates

- Mentor Program: Previous cohort members as mentors

- Certification Alignment: Map activities to certification objectives (CEH, Security+)

Technology Stack Upgrades:

- Learning Platform: Consider Canvas or Moodle for structured content delivery

- Lab Management: Explore cloud-based labs for consistency

- Collaboration Tools: Enterprise Discord or Slack for better organization

- Portfolio Platform: Professional website template for final presentations

8.3 Sustainability Model

Option 1: University Credit

- Proposal for 1-credit practicum course

- Faculty oversight, institutional resources

- Formal recognition for participants

Option 2: Club/Organization Model

- Student-run Cybersecurity Club

- Regular workshops and projects

- Lower commitment, broader participation

Option 3: Industry Partnership

- Company-sponsored training program

- Potential internship opportunities

- Real-world project experience

SECTION 9: PERSONAL REFLECTION & GROWTH

9.1 Leadership Style Evolution

Initial Approach: Directive, task-oriented
Mid-point Adjustment: More collaborative, facilitative
Final Style: Adaptive leadership based on team needs

Key Leadership Insights:

- Trust Builds Speed: Initially micromanaged, but found that trusting team accelerated progress

- Vulnerability is Strength: Admitting when I didn't know something built team cohesion

- Process Over Perfection: Consistent processes yielded better results than perfect individual work

9.2 Technical vs Managerial Balance

Initial Ratio: 70% technical, 30% managerial
Final Ratio: 30% technical, 70% managerial
Realization: The manager's greatest value is enabling others' technical work, not doing it all

9.3 Most Valuable Learnings

Technical:

- Importance of documentation standards

- Value of reproducible methodologies

- Power of collaborative troubleshooting

Managerial:

- Clear communication prevents most problems

- Regular feedback loops maintain alignment

- Celebrating small wins builds momentum

Personal:

- Capacity for leadership is greater than anticipated

- Enjoyment in facilitating others' learning

- Confidence in managing complex projects

SECTION 10: FINAL ASSESSMENT & CONCLUSION

10.1 Project Success Criteria Met

| Success Criterion | Target | Achieved | Evidence |
| --- | --- | --- | --- |
| Technical Skill Development | 3.5/5 avg | 4.2/5 avg | Pre/post assessments |
| Deliverable Quality | Professional | Excellent | Portfolio review |
| Leadership Demonstrated | Yes | Exceeded | Team feedback, artifacts |
| Career Preparation | Enhanced | Significantly | Interview materials created |
| Personal Growth | Substantial | Transformative | Self-reflection |

10.2 Return on Investment Calculation

Investment:

- Time: 68 hours

- Opportunity Cost: Other projects/courses

- Emotional Energy: High but rewarding

Returns:

- Demonstrable leadership experience

- Professional portfolio piece

- Enhanced job market position

- Peer network in cybersecurity

- Instructor recommendation potential

ROI Assessment: Highly positive - skills and artifacts will provide value for years

10.3 Final Recommendations

For Myself:

- Continue developing management skills through similar projects

- Pursue cybersecurity certifications to complement practical experience

- Maintain relationships with cohort members as professional network

For the University:

- Consider formalizing cohort-based learning models

- Invest in cybersecurity lab infrastructure

- Create pathways from coursework to practical application

For Future Students:

- Embrace collaborative learning opportunities

- Document everything - artifacts have lasting value

- Balance technical depth with management breadth

Final Assessment: Exceeds Expectations