ARTIFACT 1: PROJECT CHARTER & SYLLABUS

Shimani Alfred Tlokotsi - Cybersecurity Cohort Charter
Date: 7 December 2025
Version: 1.0

SECTION 1: EXECUTIVE OVERVIEW

Project Title: Advanced Penetration Testing Collaborative Learning Cohort
Project Sponsor: Self-Directed Professional Development Project
Project Manager: Shimani Alfred Tlokotsi
Project Duration: 5 Weeks 
Total Estimated Hours: 50+ hours per participant

Vision Statement:
To create a transformative learning environment where Bachelor of Technology students can collectively bridge the gap between academic cybersecurity theory and practical, industry-relevant penetration testing skills through structured collaboration, hands-on labs, and professional documentation standards.

Success Criteria:

- All cohort members successfully configure and maintain isolated penetration testing labs

- Production of at least 3 professional-grade penetration test reports

- Development of reusable knowledge management systems

- 100% participant satisfaction with collaborative learning model

- Portfolio development suitable for inclusion in professional resumes

SECTION 2: STAKEHOLDER REGISTER

| Role | Name | Contact | Responsibility | Engagement Level |
| --- | --- | --- | --- | --- |
| Project Manager | Shimani Alfred Tlokotsi | alfredtlokotsi@gmail.com | Overall coordination, scheduling, documentation, facilitation | High (Daily) |
| Technical Lead | Sibusiso Makhoba | 0682551658 | Advanced tool support, methodology validation | High (Weekly) |
| Documentation Lead | Abigail Mbatha | 0783256984 | Report standardization, template management | Medium-High |
| Quality Assurance | Yonelani Qinisile | 0117629873 | Peer review, methodology checking | Medium |
| Knowledge Manager | Thomas Mahlo | 0712440235 | FAQ maintenance, resource curation | Medium |

SECTION 3: SCOPE & DELIVERABLES

In-Scope:

- Virtual lab environment setup and configuration

- Three target systems: Metasploitable 2, Windows 10, Windows Server 2019

- Full penetration testing lifecycle on each target

- Collaborative report writing and peer review

- Knowledge base development and maintenance

- Weekly progress tracking and status reporting

Out-of-Scope:

- Production system testing

- Social engineering attacks

- Wireless network penetration

- Mobile application security

- Physical security assessments

Deliverables Matrix:

| Deliverable | Description | Owner | Due Date | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Lab Environment | Fully configured virtualization setup | All | Week 1 | All VMs operational, network communication established |
| Methodology Document | Standardized testing approach | Shimani Alfred Tlokotsi | Week 2 | Covers recon through reporting phases |
| Target 1 Report | Complete Metasploitable assessment | Team | Week 4 | Includes all phases, screenshots, remediation |
| Target 2 Report | Windows 10 assessment | Team | Week 4 | Covers Windows-specific techniques |
| Consolidated Portfolio | GitHub repository with all artifacts | Shimani Alfred Tlokotsi | Week 5 | Organized, documented, professional presentation |
| Retrospective Analysis | Lessons learned document | All | Week 5 | Covers technical and collaborative aspects |

SECTION 4: DETAILED SCHEDULE & MILESTONES

Week-by-Week Breakdown:

WEEK 1: FOUNDATION & ORIENTATION

- Kickoff Meeting: Agenda includes introductions, goal setting, tool review

- Lab Requirements: Minimum 16GB RAM, 200GB storage, virtualization enabled

- Software Stack: VirtualBox 7.0+, Kali Linux 2023.3, Windows ISOs, Metasploitable 2

- Network Design: [Include diagram of proposed virtual network]

- Success Check: All members can ping between VMs by Friday

WEEK 2: METHODOLOGY & RECONNAISSANCE

- Focus Areas: OSINT techniques, passive reconnaissance, active scanning methodology

- Tools: Nmap, Netdiscover, whois, dig, Shodan (free account)

- Collaborative Task: Each member researches different reconnaissance tools

- Deliverable: Reconnaissance checklist and tool comparison matrix

WEEK 3: SCANNING & ENUMERATION

- Technical Depth: Nmap scripting engine, service fingerprinting, vulnerability scanning

- Tools: Nmap advanced scripts, Nikto, Enum4linux, SNMPwalk

- Lab Exercise: Full port scan with service detection on all targets

- Deliverable: Service enumeration report for each target system

WEEK 4: VULNERABILITY ANALYSIS & EXPLOITATION

- Methodology: CVE research, exploit selection, safe testing procedures

- Tools: Metasploit Framework, Searchsploit, Exploit-DB

- Ethical Considerations: Discussion of responsible disclosure

- Deliverable: Vulnerability assessment matrix with risk ratings

WEEK 4: POST-EXPLOITATION & REPORTING

- Techniques: Privilege escalation, persistence, lateral movement

- Tools: Meterpreter, PowerSploit, Mimikatz (in lab only)

- Documentation: Report structure, executive summary writing

- Deliverable: First complete penetration test report

WEEK 5: ADVANCED TOPICS & TEAM COLLABORATION

- Focus: Windows-specific attacks, AV evasion basics, clearing tracks

- Collaboration: Cross-review of reports, methodology refinement

- Team Challenge: Capture-the-flag style exercise

- Deliverable: Second report and peer review feedback

WEEK 5: CONSOLIDATION & KNOWLEDGE TRANSFER

- Portfolio Development: GitHub organization, README creation

- Retrospective: What worked, what didn't, lessons learned

- Knowledge Transfer: Creating guide for next cohort

- Final Deliverable: Complete project portfolio and final presentation

SECTION 5: COMMUNICATION PLAN

Regular Meetings:

- Weekly Sync: Wednesdays 7:00 PM via Discord

- Duration: 60-90 minutes

- Format: Roundtable updates, technical deep dive, Q&A

- Recording: Sessions recorded and stored in shared drive

Communication Channels:

- Primary: Discord Server with channels: general, #technical-help, #report-review, #resources

- Secondary: Email for formal notifications

- Documentation: Google Drive for collaborative editing

- Code/Artifacts: GitHub repository

Reporting Structure:

- Daily: Informal check-ins via Discord

- Weekly: Status report due each Monday at 9:00 AM

- Milestone: Formal review at end of Weeks 2, 4, and 5

SECTION 6: RISK REGISTER

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| R01 | Technical difficulties with lab setup | High | Medium | Create detailed setup guide, offering one-on-one support sessions | Shimani Alfred Tlokotsi |
| R02 | Participant drop-off | Medium | High | Regular check-ins, engaging content, peer accountability | Shimani Alfred Tlokotsi |
| R03 | Scope creep | Medium | Medium | Clear charter, weekly scope review, change control | Shimani Alfred Tlokotsi |
| R04 | Knowledge gaps slowing progress | High | Medium | Pre-assessment, just-in-time training, buddy system | Technical Lead |
| R05 | Time constraints | High | High | Realistic scheduling, flexible meeting options, prioritized tasks |  |